## Slide 1
Page 13
Project Progress #2 Presentation
TailTales
  Report Date - March 12, 2025
  Professor – Abidin Akkok
Team Members
  Haroon Ahmed Bajwa
  Aryan Tuwar
  Vivian Zhonghui Liu
  Mrinaal Nagpal

## Slide 2
TailTalis
Page 8
Overview
TailTales has moved forward into the second phase, focusing on refining core features, improving user experience, and ensuring system stability. Key developments include backend optimizations, UI enhancements, and additional functionality for seamless user interaction.

## Slide 5
TailTales
Page 6
Summary of Performance
✅ Intuitive Navigation
✅ Well-structured Shop Section
✅ Dynamic Trending Products
✅ Engaging Our Story Page
✅ Progress steady, but pending tasks need completion

## Slide 7
Milestone | Planned Date | Actual Date | Status
Footer | February 12, 2025 | February 18, 2025 | ✅ Completed
HeroSection | February 12, 2025 | February 18, 2025 | ✅ Completed
Navbar | February 12, 2025 | February 18, 2025 | ✅ Completed
OurStory | February 12, 2025 | March 11, 2025 | ✅ Completed
ShopInfo | February 12, 2025 | March 11, 2025 | ✅ Completed
TrendingProucts | February 12, 2025 | February 18, 2025 | ✅ Completed
AppointmentSection | February 12, 2025 | - | ⏳ In Progress
BlogSection | February 12, 2025 | - | ⏳ In Progress
CartPage | February 12, 2025 | - | ⏳ In Progress
ProfilePage | February 12, 2025 | - | ⏳ In Progress
SignupSection | February 12, 2025 | - | ⏳ In Progress
Key Milstones

## Slide 8
TailTales
Page 11
Planned Work for Next Period
Finalizing Sections
•Appointment, Blog, Cart, Profile, Signup
Enhancements & Optimization
  UI improvements
  Performance tuning
  Backend efficiency
QA & Testing
  Internal tests
  User feedback
  Bug fixes

## Slide 9
Issue | Description | Status | Assigned To
Navbar responsiveness | Navbar layout breaks on smaller screens | Resolved | Aryan Tuwar
Cart functionality | Users unable to update quantity in cart | In Progress | Aryan Tuwar
Slow API response | Backend APIs taking longer than expected | Pending | Haroon Ahmed Bajwa
Profile page loading | Page fails to load on certain browsers | Testing | Mrinaal Nagpal
TailTales
Page 14
High-Priority Issues
Delayed sections need completion
Pending UI/UX bug fixes
Backend optimizations required
Better Jira task management

## Slide 10
Conclusions
TailTales
Page 10
✔ Progress steady, some sections incomplete
✔ High-priority issues actively addressed
✔ Focus: Completing sections & optimization
✔ On track to meet final project deadline